## Worksheet
Audit Preparation - Project Timeline
Phase | Task Description | Responsible Party | Start Date | End Date | Status
Preparation Phase | Define audit scope and objectives | Project Manager | 2024-04-01 | 2024-04-05 | In Progress
| Identify key stakeholders and contacts | Internal Audit Team | 2024-04-06 | 2024-04-10 | Pending
| Gather preliminary documentation and records | Records Coordinator | 2024-04-11 | 2024-04-15 | Pending
Execution Phase | Conduct initial risk assessment | Risk Analyst | 2024-04-16 | 2024-04-20 | Pending
| Perform on-site review and testing of processes | Audit Team Lead | 2024-04-21 | 2024-04-30 | Pending
| Document findings and evidence collection | Audit Specialists | 2024-05-01 | 2024-05-10 | Pending
Reporting Phase | Compile audit findings into draft report | Report Writer | 2024-05-11 | 2024-05-15 | Pending
| Share draft findings with stakeholders for feedback | Project Manager | 2024-05-16 | 2024-05-18 | Pending
| Finalize audit report and submit to management | Audit Director | 2024-05-19 | 2024-05-21 | Pending
Follow-Up Phase | Review action plans from management response | Compliance Officer | 2024-05-22 | 2024-05-31 | Pending
| Verify implementation of corrective actions | Audit Follow-Up Team | 2024-06-01 | 2024-06-15 | Pending
| Closed audit with final sign-off and archiving | Project Manager & Audit Director | 2024-06-16 | 2024-06-17 | Pending
Audit Preparation - Project Timeline ¦ Prepared on April 5, 2024 ¦ One Page Version