## Worksheet
Audit Preparation - Project Timeline
Template Type: Project Timeline
Purpose: Audit Preparation
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person
Planning & Scope Definition
Phase 1 | Define audit objectives and scope | 2024-01-05 | 2024-01-12 | In Progress | Jane Smith (Audit Lead)
Documentation Collection
Phase 2 | Gather financial records and compliance documents | 2024-01-15 | 2024-01-31 | Pending | Finance Team (John Doe)
Internal Review & Validation
Phase 3 | Conduct internal review of collected data | 2024-02-01 | 2024-02-15 | Pending | Audit Team (Sarah Lee)
Audit Execution & Findings
Phase 4 | Perform on-site audit and document findings | 2024-02-18 | 2024-03-05 | Pending | Audit Team (Mark Taylor)
Reporting & Follow-up
Phase 5 | Prepare audit report and share with stakeholders | 2024-03-08 | 2024-03-15 | Pending | Jane Smith (Audit Lead)
Closure & Recommendations Implementation
Phase 6 | Review audit findings and implement corrective actions | 2024-03-18 | 2024-04-15 | Pending | All Departments (Lead: Alex Johnson)
Next Review Date:April 18, 2024