## Worksheet
Audit Preparation - Project Timeline (Planning View)
Task ID | Task Description | Responsible Party | Start Date | End Date | Status
T001 | Audit Planning Kick-off Meeting | Project Manager, Audit Lead | 2023-10-05 | 2023-10-05 | In Progress
T002 | Identify Audit Scope & Objectives | Audit Lead, Finance Director | 2023-10-06 | 2023-10-10 | In Progress
T003 | Compile Preliminary Documentation | Finance Team, Compliance Officer | 2023-10-11 | 2023-10-17 | To Do
T004 | Risk Assessment & Materiality Evaluation | Audit Team, Internal Controls Specialist | 2023-10-18 | 2023-10-24 | To Do
T005 | Audit Plan Finalization & Approval | Audit Lead, CFO, Legal Counsel | 2023-10-25 | 2023-10-31 | To Do
T006 | Audit Fieldwork Preparation (Checklists & Tools) | Audit Team, IT Support | 2023-11-01 | 2023-11-07 | To Do
T007 | Audit Fieldwork Execution (Phase 1) | Audit Team, Department Heads | 2023-11-08 | 2023-11-29 | To Do
T008 | Audit Fieldwork Execution (Phase 2) | Audit Team, Department Heads | 2023-11-30 | 2023-12-15 | To Do
T009 | Interim Audit Findings Review Meeting | Audit Lead, Management Team | 2023-12-16 | 2023-12-18 | To Do
T010 | Audit Report Drafting & Review | Audit Lead, Compliance Team | 2023-12-19 | 2024-01-05 | To Do
T011 | Audit Report Final Approval & Sign-off | CFO, Audit Committee Chair | 2024-01-06 | 2024-01-12 | To Do
T012 | Audit Closure & Post-Audit Review Meeting | Project Manager, Audit Lead | 2024-01-13 | 2024-01-15 | To Do
Note:This is a planning view of the audit preparation timeline. Actual dates and statuses may be updated as the project progresses.