## Worksheet
Audit Preparation - Project Timeline
Task ID | Task Description | Responsible Team | Start Date | End Date | Status
T001 | Define Audit Scope & Objectives | Audit Team Lead | 2024-04-01 | 2024-04-05 | In Progress
T002 | Review Prior Audit Findings | Audit Analysts | 2024-04-06 | 2024-04-10 | Pending
T003 | Collect Supporting Documentation | Department Heads | 2024-04-11 | 2024-04-18 | Pending
T004 | Perform Risk Assessment & Planning | Audit Team Lead | 2024-04-19 | 2024-04-23 | Pending
T005 | Fieldwork: Data Collection & Testing | Audit Staff | 2024-04-24 | 2024-05-15 | Pending
T006 | Initial Draft of Audit Report | Audit Analysts | 2024-05-16 | 2024-05-18 | Pending
T007 | Management Review & Feedback | Stakeholders / Management | 2024-05-19 | 2024-05-23 | Pending
T008 | Finalize Audit Report & Approval | Audit Team Lead | 2024-05-24 | 2024-05-31 | Pending
Total Duration: |  |  |  |  | 60 days