## Worksheet
Phase / Task | Start Date | End Date | Status | Responsible Team/Person | Notes / Milestones
Planning & Scope Definition | 2023-10-01 | 2023-10-15 | In Progress | Project Lead, Audit Team | Finalize audit scope and objectives.
Data Collection & Documentation Gathering | 2023-10-16 | 2023-11-05 | Pending | Finance & Operations Teams | All financial records and compliance documents to be submitted.
Risk Assessment & Prioritization | 2023-11-06 | 2023-11-15 | Pending | Risk Management Unit | Identify high-risk areas for audit focus.
Internal Review & Gap Analysis | 2023-11-16 | 2023-11-30 | Pending | Audit Team, Legal Counsel | Review findings and identify control gaps.
Stakeholder Coordination & Scheduling | 2023-12-01 | 2023-12-10 | Pending | CxO Office, Audit Lead | Align audit calendar with key executives.
Audit Execution & Fieldwork | 2023-12-11 | 2024-01-15 | Pending | Audit Team, External Consultants | On-site and remote audit activities.
Reporting & Findings Compilation | 2024-01-16 | 2024-01-31 | Pending | Audit Report Team | Draft report with recommendations and action plans.
Management Review & Feedback | 2024-02-01 | 2024-02-15 | Pending | Senior Management, Compliance Committee | Draft feedback and validation of audit results.
Final Audit Report & Approval | 2024-02-16 | 2024-03-01 | Pending | Audit Director, Board of Directors | Finalize and present report to leadership.
Follow-up & Corrective Action Tracking | 2024-03-02 | 2024-06-30 | Pending | Compliance & Audit Teams | Monitor implementation of corrective actions.