## Worksheet
Audit Preparation - Project Timeline
Phase | Task Description | Responsible Team/Person | Start Date | End Date | Status
Planning & Scoping | Define audit objectives and scope. | Audit Lead, Management | 2024-01-01 | 2024-01-15 | Pending
Data Collection | Gather financial and operational records. | Finance, Operations Team | 2024-01-16 | 2024-02-15 | In Progress
Document Review | Analyze policies, procedures, and compliance documents. | Audit Team | 2024-02-16 | 2024-03-15 | Not Started
Fieldwork & Testing | Perform testing and validation of key controls. | Audit Team, IT Department | 2024-03-16 | 2024-04-30 | Not Started
Findings & Reporting | Draft audit findings and report. | Audit Lead, Internal Review Team | 2024-05-01 | 2024-05-15 | Not Started
Management Response | Review and respond to audit findings. | Department Heads, Management | 2024-05-16 | 2024-05-31 | Not Started
Closure & Follow-up | Confirm corrective actions and close audit. | Audit Lead, Compliance Team | 2024-06-01 | 2024-06-15 | Not Started