## Worksheet
Task | Responsible Person | Start Date | End Date | Status
Define audit scope and objectives | Finance Manager | 2024-03-01 | 2024-03-05 | In Progress
Gather financial records and documentation | Accountant I | 2024-03-06 | 2024-03-15 | Pending
Review internal controls and processes | Internal Auditor | 2024-03-16 | 2024-03-25 | Pending
Conduct preliminary risk assessment | Risk Manager | 2024-03-18 | 2024-03-28 | Pending
Schedule audit team meetings and reviews | Project Coordinator | 2024-03-19 | 2024-03-31 | Pending
Finalize audit plan and checklist | Audit Lead | 2024-04-01 | 2024-04-05 | Pending
Perform fieldwork and data collection | Audit Team | 2024-04-06 | 2024-04-15 | Pending
Analyze findings and draft report | Audit Analysts | 2024-04-16 | 2024-04-25 | Pending
Review and validate audit conclusions | Senior Auditor | 2024-04-26 | 2024-05-01 | Pending
Submit final audit report to management | Audit Lead | 2024-05-02 | 2024-05-03 | Pending