## Worksheet
Startup Project Timeline - Audit Preparation
Phase | Task Description | Responsible Team | Scheduled Start Date | Scheduled End Date
Phase 1: Planning & Preparation
1.1 | Define audit scope and objectives | Leadership & Finance Team | 2024-04-01 | 2024-04-05
1.2 | Assemble audit readiness task force | HR & Operations | 2024-04-06 | 2024-04-10
Phase 2: Document Collection & Review
2.1 | Gather all financial and operational records | Finance & Legal Teams | 2024-04-11 | 2024-04-18
2.2 | Organize and index documents for audit access | Admin & Compliance Team | 2024-04-19 | 2024-04-25
Phase 3: Internal Review & Gap Analysis
3.1 | Conduct internal audit of records and compliance status | Compliance Team | 2024-04-26 | 2024-05-03
3.2 | Identify and resolve gaps in documentation and procedures | All Departments | 2024-05-04 | 2024-05-11
Phase 4: Final Readiness & Audit Execution
4.1 | Final document verification and sign-off | CFO & Legal Counsel | 2024-05-12 | 2024-05-15
4.2 | Host external audit kickoff meeting and begin review process | Audit Team & Leadership | 2024-05-16 | 2024-05-31