## Worksheet
Audit Preparation - Project Timeline Summary View
Phase | Task Description | Responsible Team | Start Date | End Date | Status
Phase 1: Planning & Scoping | Define audit objectives, scope, and key stakeholders. | Project Lead, Audit Manager | 2024-04-01 | 2024-04-15 | Completed
Phase 2: Document Collection | Gather financial records, compliance documents, and process manuals. | Documentation Team | 2024-04-16 | 2024-05-10 | In Progress
Phase 3: Internal Review | Conduct preliminary review of documents and identify gaps. | Internal Audit Team | 2024-05-11 | 2024-05-25 | Pending
Phase 4: Fieldwork & Testing | Perform on-site testing, interviews, and evidence verification. | Audit Field Team | 2024-05-26 | 2024-06-15 | Pending
Phase 5: Report Drafting | Compile findings, draft audit report, and recommend actions. | Reporting Team | 2024-06-16 | 2024-06-30 | Pending
Phase 6: Final Approval & Submission | Review and approve final report with leadership. | Executive Management, Audit Committee | 2024-07-01 | 2024-07-15 | Pending