## Worksheet
Audit Preparation - Project Timeline (Team Use)
Phase | Task Description | Responsible Team Member(s) | Start Date | End Date | Status
Phase 1: Planning | Define audit scope and objectives | John Smith, Lisa Chen | 2023-10-01 | 2023-10-05 | Pending
| Identify key stakeholders and contacts | Sarah Johnson, Mark Lee | 2023-10-06 | 2023-10-10 | In Progress
| Develop audit checklist and documentation requirements | Lisa Chen, John Smith | 2023-10-11 | 2023-10-15 | Not Started
Phase 2: Data Collection | Gather financial records and transaction logs | Mark Lee, Emily Davis | 2023-10-16 | 2023-10-25 | In Progress
| Collect HR and compliance documentation | Sarah Johnson, Alex Rivera | 2023-10-18 | 2023-10-30 | In Progress
| Review IT system access and audit trails | David Kim, Priya Patel | 2023-10-20 | 2023-11-05 | Not Started
| Compile all collected data for review | All Team Members | 2023-11-06 | 2023-11-10 | Not Started
Phase 3: Review & Analysis | Conduct preliminary review of financial data accuracy | Lisa Chen, Emily Davis | 2023-11-11 | 2023-11-20 | Not Started
| Identify discrepancies and high-risk areas | John Smith, David Kim | 2023-11-21 | 2023-11-30 | Not Started
| Prepare draft findings and recommendations | All Team Members | 2023-12-01 | 2023-12-05 | Not Started
Phase 4: Reporting | Finalize audit report with supporting evidence | Lisa Chen, Sarah Johnson | 2023-12-06 | 2023-12-15 | Not Started
| Presentation preparation for management review | Mark Lee, Alex Rivera | 2023-12-16 | 2023-12-20 | Not Started
| Distribute final audit report and follow-up actions | All Team Members | 2023-12-21 | 2023-12-31 | Not Started
Total Tasks: |  |  |  |  | 14