## Worksheet
Audit Preparation - Project Timeline
Purpose:Audit Preparation
Template Type:Project Timeline
Style/Version:Template Version 2.0
Phase | Task Description | Start Date | End Date | Status | Responsible Team
Planning & Scope Definition | Define audit objectives, scope, and key stakeholders. | 2024-04-01 | 2024-04-05 | In Progress | Audit Team Lead
Data Collection Preparation | Prepare documentation and data request templates. | 2024-04-06 | 2024-04-10 | Pending | Data Management Unit
Internal Document Review | Review existing policies, procedures, and compliance records. | 2024-04-11 | 2024-04-18 | Pending | Internal Compliance Team
Audit Fieldwork - Phase 1 | Conduct on-site assessments and interviews. | 2024-04-19 | 2024-05-03 | Pending | Audit Field Team
Audit Fieldwork - Phase 2 | Verify data accuracy and test control effectiveness. | 2024-05-06 | 2024-05-17 | Pending | Audit Field Team
Findings Documentation & Validation | Document audit findings and validate with relevant departments. | 2024-05-18 | 2024-05-25 | Pending | Audit Team Lead, Department Heads
Final Report Preparation | Compile audit findings into a formal report with recommendations. | 2024-05-26 | 2024-06-01 | Pending | Audit Team Lead, Reporting Specialist
Management Review & Approval | Submit report for senior management review and sign-off. | 2024-06-02 | 2024-06-07 | Pending | Executive Management
Audit Closure & Follow-Up Planning | Celebrate audit closure and initiate action plan tracking. | 2024-06-08 | 2024-06-15 | Pending | Audit Team, Operations Lead
© 2024 Audit Preparation Template ¦ Version 2.0 ¦ For Internal Use Only