## Worksheet
Audit Preparation - Project Timeline (Tracking View)
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | % Complete
T001 | Define Audit Scope and Objectives | Lead Auditor | 2023-10-05 | 2023-10-15 | On Track | 95%
T002 | Gather Financial Records (Q3) | Finance Team | 2023-10-16 | 2023-11-05 | In Progress | 65%
T003 | Review Internal Controls Documentation | Risk & Compliance | 2023-11-06 | 2023-11-25 | In Progress | 45%
T004 | Conduct Preliminary Risk Assessment | Audit Team Lead | 2023-11-26 | 2023-12-15 | Not Started | 0%
T005 | Develop Audit Plan and Checklist | Audit Planning Group | 2023-12-16 | 2024-01-15 | Not Started | 0%
T006 | Fieldwork Execution - Department A & B | Audit Team - Fieldwork | 2024-01-16 | 2024-02-15 | Not Started | 0%
T007 | Compile Audit Findings and Draft Report | Audit Analysts | 2024-02-16 | 2024-03-15 | Not Started | 0%
T008 | Review and Approve Final Audit Report | Audit Committee | 2024-03-16 | 2024-03-31 | Not Started | 0%
Prepared for Audit Preparation ¦ Project Timeline (Tracking View) ¦ Updated on October 5, 2023