## Worksheet
Audit Preparation - Project Tracker (Extended)
Project Status Overview
Project ID | Project Name | Department | Lead Auditor | Status | Start Date | Target Completion Date | Actual Completion Date | Risk Level
PROJ-001 | Financial Statement Audit - Q1 2024 | Finance | Sarah Johnson | In Progress | 2024-01-15 | 2024-03-31 | -- | High
PROJ-002 | IT System Security Review | IT Department | Michael TorresPending Approval | 2024-01-10 | 2024-04-30 | -- | Medium
PROJ-003 | HR Compliance Audit | Human ResourcesRachel KimCompleted | 2024-01-05 | 2024-03-15 | 2024-03-15 | Low
PROJ-004 | Supply Chain Risk AssessmentProcurementLiam BrownDelayed (Pending Vendor Data) | 2024-01-20 | 2024-05-15 | -- | High
PROJ-005 | EHS Compliance Audit (Facility A)OperationsAmanda PatelIn Progress | 2024-02-01 | 2024-04-30 | -- | Medium
PROJ-006 | Sales Process Compliance CheckSales & MarketingNathan WrightPending Review | 2024-01-30 | 2024-03-31 | -- | Low
PROJ-007 | Data Privacy & GDPR ComplianceIT Security & LegalClaire DuboisIn Progress | 2024-01-15 | 2024-06-30 | -- | High
Total Projects:7 ¦Completed:1 ¦In Progress:3 ¦Pending:2 ¦Delayed:1