## Worksheet
Audit Preparation - Project Tracker (Planning View)
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | Prioritization Level
TASK-001 | Review financial statements for Q1 2024 | Finance Team | 2024-03-15 | 2024-03-31 | In Progress | High
TASK-002 | Verify compliance with SOX controls | Internal Audit Team | 2024-03-18 | 2024-04-15 | Pending
TASK-003 | Update audit checklist documentation | Compliance Officer | 2024-03-16 | 2024-03-31 | Completed
TASK-004 | Conduct department interviews (HR, IT) | Audit Lead | 2024-03-25 | 2024-04-10 | Pending
TASK-007 | Review and approve audit findings with stakeholders | Audit Committee2024-05-16 | 2024-05-31 | Pending