## Worksheet
Weekly Project Tracker - Audit Preparation
Week Ending | Task Description | Responsible Team Member | Status | Progress (%) | Notes/Comments
2023-10-06 | Review financial records for Q3 2023 | Sarah Johnson | In Progress | 75% | Finalizing reconciliations with bank statements.
2023-10-06 | Prepare audit checklist for internal review | Michael Chen | Pending | 10% | Pending approval from compliance team.
2023-10-06 | Conduct internal control testing | Lisa Patel | In Progress | 45% | Completed 3 out of 7 test procedures.
2023-10-06 | Document audit evidence for payroll processes | James Wilson | Completed | 100% | All documentation reviewed and approved.
2023-10-13 | Review procurement policies for compliance | Amy Rodriguez | Pending | 0% | To be initiated after policy review.
Legend:
Pending– Task not yet started.
In Progress– Task currently being worked on.
Completed– Task successfully finished.