## Worksheet
Audit Preparation - Schedule Planner (Advanced)
Task ID | Task Description | Responsible Team/Person | Start Date | End Date | Status | Prioritization Level
AP-001 | Initial Risk Assessment & Planning | Audit Team Lead | 2023-10-05 | 2023-10-12 | High Priority | Critical
AP-002 | Gather Financial Statements (FY2023) | Finance Department | 2023-10-13 | 2023-10-19 | In Progress | Critical
AP-003 | Review Internal Controls Documentation | Compliance Officer | 2023-10-20 | 2023-11-05 | High Priority | Critical
AP-004 | Conduct Site Walkthroughs & Interviews | Audit Team - Field Staff | 2023-11-06 | 2023-11-17 | Not Started | High
AP-005 | Test Key Controls & Analytical Procedures | Audit Senior Team | 2023-11-18 | 2023-12-08 | High Priority | Critical
AP-006 | Document Findings & Prepare Draft Report | Audit Lead Analysts | 2023-12-09 | 2023-12-18 | Not Started | High
AP-007 | Management Review & Feedback Session | Executive Team & Audit Committee | 2023-12-19 | 2023-12-26 | High Priority | Critical
AP-008 | Finalize Audit Report & Issue Clearance | Audit Manager & Legal Counsel | 2023-12-27 | 2024-01-05 | Pending Approval | Medium
Prepared by:Audit Planning Office ¦Date:October 5, 2023
Note: This schedule is subject to change based on audit scope adjustments or stakeholder feedback.