## Worksheet
Audit Preparation - Schedule Planner (Analysis View)
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
A001 | Review financial statements for Q4 2023 | Finance Team | 2024-03-15 | 2024-03-31 | In Progress | 65%
A002 | Verify fixed asset records | Accounting Department | 2024-03-18 | 2024-04-15 | In Progress | 55%
A003 | Conduct internal controls assessment | Risk & Compliance Unit | 2024-04-15 | 2024-05-15 | Delayed | 30%
A004 | Prepare audit working papers | Audit Team Lead | 2024-05-16 | 2024-06-30 | Complete | 100%
A005 | Coordinate with external auditors | Internal Audit Manager | 2024-06-15 | 2024-07-31 | In Progress | 75%
A006 | Finalize audit report draft | Audit Director | 2024-08-15 | 2024-10-31 | Delayed | 45%
A007 | Review and approve final audit report | Executive Committee | 2024-11-15 | 2024-12-31 | Complete | 98%
A008 | Archive audit documentation | Records Manager | 2024-12-15 | 2024-12-31 | Complete | 95%
Summary:Total Tasks: 8 ¦ Completed: 3 ¦ In Progress: 3 ¦ Delayed: 2