## Worksheet
Audit Preparation Schedule Planner
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Priority
TASK-001 | Initial Risk Assessment | Risk Management Team | 2023-10-01 | 2023-10-15 | In Progress | High
TASK-002 | Document Collection & Organization | Compliance Officer | 2023-10-16 | 2023-11-05 | Pending Review | High
TASK-003 | Data Validation and Reconciliation | Finance Team Lead | 2023-11-06 | 2023-11-25 | In Progress | High
TASK-004 | Internal Audit Testing Phase 1 | Audit Internal Team | 2023-11-26 | 2023-12-15 | Pending Review | High
TASK-005 | Management Response & Action Planning | Department Heads | 2023-12-16 | 2023-12-31 | Pending Review | Medium
TASK-006 | Final Audit Report Drafting & Approval | Audit Lead & Comptroller | 2024-01-01 | 2024-01-15 | Pending Review | High
TASK-007 | Audit Closure and Follow-Up Plan Finalization | Compliance & Audit Committee | 2024-01-16 | 2024-01-31 | Pending Review | Medium
Audit Preparation Schedule Planner v2.1 – Business Use ¦ Prepared on October 26, 2023