## Worksheet
AUDIT PREPARATION - SCHEDULE PLANNER (COMPACT)
Task ID | Activity | Responsible Person | Due Date | Status | Notes
AUD-001 | Document Collection Review | J. Smith | 2023-10-05 | Pending | Review all financial records.
AUD-002 | Interview Team Leads | L. Johnson | 2023-10-07 | In Progress | Schedule sessions with department heads.
AUD-003 | Risk Assessment Draft | M. Brown | 2023-10-10 | Pending | Identify key control points.
AUD-004 | Data Validation Test | R. Davis | 2023-10-12 | Not Started | Run sample data checks.
AUD-005 | Audit Plan Finalization | S. Wilson | 2023-10-14 | Pending | Submit for management approval.
Total Tasks: |  |  |  |  | 5