## Worksheet
Audit Preparation - Schedule Planner (Data Version)
Task ID | Task Description | Responsible Party | Start Date | Due Date | Status | % Complete
TA001 | Review Financial Statements | Finance Team | 2024-04-01 | 2024-04-15 | Pending | 0%
TA002 | Collect Supporting Documentation | Audit Team Lead | 2024-04-16 | 2024-05-15 | In Progress | 65%
TA003 | Perform Internal Controls Testing | Risk & Compliance | 2024-05-16 | 2024-06-15 | Pending | 0%
TA004 | Clean Up Data Anomalies | Data Team | 2024-06-16 | 2024-07-15 | Pending | 0%
TA005 | Finalize Audit Report Draft | Audit Lead | 2024-07-16 | 2024-07-31 | Pending | 0%
Total Tasks:5 ¦Completed:0 ¦In Progress:1 ¦Pending:4
Last Updated: April 5, 2024 ¦ Version: Data Version v1.0