## Worksheet
Audit Preparation - Schedule Planner (Extended Version)
# | Task Description | Responsibility & Status |  |  |  |  | Timeline & Milestones
|  | Owner | Team | Status |  |  | Due Dates (YYYY-MM-DD)
|  |  |  | Planned | Actual | Progress (%) | Start Date | Target End | Actual End
1 | Initial Planning Meeting Define audit scope, objectives, and key stakeholders. | Jane Doe | Audit Team | In Progress | - | 85% | 2024-03-15 | 2024-03-17 | -
2 | Document Collection Gather all relevant financial, operational, and compliance documents. | John Smith | Support Team | Pending Review | -< th style="text-align:center;">2024-03-18< th style="text-align:center;">2024-03-31< th style="text-align:center;">-
3 | Review Internal Controls Analyze current control mechanisms and identify gaps. | Alice Brown | Compliance Team | In Progress | 2024-04-15 | th style="text-align:center;">-< th style="text-align:center;">75%< th style="text-align:center;">2024-03-312024-04-15 | -
4 | Risk Assessment Workshop Identify and prioritize key audit risks. | Robert Lee | Risk & Audit Team | Not Started | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-04-182024-04-19 | -
5 | Fieldwork Preparation Prepare checklists, templates, and interview guides. | Susan Clark | Audit Team Lead | Not Started | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-04-162024-04-25 | -
6 | Fieldwork Execution Conduct on-site or remote audit procedures. | Michael Evans | Audit Team (Remote) | Pending | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-04-282024-05-17 | -
7 | Management Review Meeting Draft findings for discussion with management. | Lisa Young | Audit Team + Leadership | Pending | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-05-182024-05-19 | -
8 | Final Audit Report Drafting Compile all findings, recommendations, and conclusions. | David Turner | Audit Team Lead | Pending | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-05-202024-05-31 | -
9 | Final Review & Approval Review report by Internal Audit Committee. | Elena Perez | Internal Audit Committee | Pending | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-06-012024-06-15 | -
10 | Report Distribution & Follow-up Plan Deliver final report and set action item timelines. | Grace Kim | Audit Team + Executives | Pending | - | < th style="text-align:center;">-< th style="text-align:center;">0%< th style="text-align:center;">2024-06-162024-06-30 | -
Total Tasks: |  |  | 10 |  |  |  |  | Overall Progress: 27%
Note:This schedule is subject to change. Update status bi-weekly. All dates are tentative unless confirmed by the audit lead.