## Worksheet
Audit Preparation - Schedule Planner (Manager View)
Task ID | Task Description | Responsible Team | Start Date | Due Date | Status | % Complete
T001 | Collect Financial Statements for Q2 2024 | Finance Department | 2024-04-15 | 2024-05-10 | In Progress | 75%
T002 | Review Internal Controls Documentation | Compliance Team | 2024-04-18 | 2024-05-15 | In Progress | 60%
T003 | Conduct Preliminary Risk Assessment | Risk Management | 2024-04-16 | 2024-05-18 | Pending | 15%
T004 | Prepare Audit Checklist Template | Audit Team Lead | 2024-04-17 | 2024-05-13 | Completed | 100%
T005 | Coordinate with External Auditor (Initial Meeting) | Audit Coordinator | 2024-04-19 | 2024-05-17 | In Progress | 80%
T006 | Review IT System Access Logs (Past 3 Months) | IT Security Team | 2024-04-21 | 2024-05-19 | Pending | 5%
Total Tasks:6 ¦In Progress:3 ¦Pending:2 ¦Completed:1