## Worksheet
Audit Preparation - Schedule Planner
Phase 1: Planning & ScopingPrepared on: October 26, 2023
Task ID | Task Description | Responsible Party | Due Date | Status
AUD-001 | Define audit scope and objectives | Lead Auditor | 2023-11-05 | Pending
AUD-002 | Identify key areas for review (financial, operational, compliance) | Audit Team | 2023-11-08 | In Progress
Internal Stakeholder Engagement
AUD-003 | Schedule kickoff meeting with department heads | Project Manager | 2023-11-06 | Pending
AUD-004 | Distribute audit questionnaire to relevant departments | Internal Coordinator | 2023-11-07 | Pending
Documentation & Tools Setup
AUD-005 | Set up shared audit repository (cloud-based) | IT Support | 2023-11-04 | Completed
Risk Assessment & Prioritization
AUD-006 | Conduct preliminary risk assessment matrix review | Risk Analyst | 2023-11-09 | Pending
Phase 2: Fieldwork PreparationPrepared on: October 26, 2023
Task ID | Task Description | Responsible Party | Due Date | Status
AUD-011 | Review prior audit reports and findings (2022–2023) | Audit Senior | 2023-11-13 | Pending
Evidence Collection Planning
AUD-012 | Develop detailed evidence collection plan by department | Team Lead (Finance) | 2023-11-14 | Pending
AUD-013 | Create checklist for transaction sampling and testing procedures | Audit Specialist (Compliance) | 2023-11-15 | Pending
Training & Readiness Checks
AUD-014 | Conduct internal training session on audit procedures and tools | Lead Auditor | 2023-11-12 | Pending
Logistics Coordination
AUD-015 | Confirm auditor travel arrangements and on-site access permissions | Admin Coordinator | 2023-11-10 | Pending
Phase 3: Fieldwork ExecutionPrepared on: October 26, 2023
Task ID | Task Description | Responsible Party | Dates (Start–End) | Status
AUD-021 | Conduct on-site audit at Finance Department (Q3 2023) | Finance Audit Team | 2023-11-16 – 2023-11-18 | In Progress
Departmental Reviews (Continuing)
AUD-022 | Operational Audit – Supply Chain Division (Q3 2023) | Operations Auditor | 2023-11-19 – 2023-11-24 | Pending
AUD-023 | IT & Cybersecurity Audit (Network Access Controls) | IT Auditor | 2023-11-25 – 2023-11-30 | Pending
Daily Reporting & Issue Tracking
AUD-024 | Submit daily fieldwork log and draft findings to Lead Auditor | All Auditors | Daily (11/16 – 12/05) | Pending
Ad-hoc Investigations & Escalations
AUD-025 | Investigate flagged transaction anomalies (Sample #789, 11/20) | Lead Auditor | 2023-11-20 – 2023-11-23 | Pending
Phase 4: Reporting & CloseoutPrepared on: October 26, 2023
Task ID | Task Description | Responsible Party | Dates (Start–End) | Status
AUD-031 | Consolidate findings from all departments into draft report | Lead Auditor | 2023-12-06 – 2023-12-10 | Pending
Draft Report Development
AUD-032 | Prepare executive summary and key recommendations section | Report Writer (Compliance) | 2023-12-11 – 2023-12-14 | Pending
Internal Review & Feedback Loop
AUD-033 | Share draft report with audit committee and obtain feedback | Project Manager | 2023-12-15 – 2023-12-18 | Pending
Final Report & Approval Process
AUD-034 | Revise report based on feedback; obtain final sign-off from Head of Audit | Lead Auditor | 2023-12-19 – 2023-12-25 | Pending
Audit Closeout & Follow-up Planning
AUD-035 | Conduct final closeout meeting with management teams | Lead Auditor & Manager | 2023-12-26 – 2023-12-31 | Pending
AUD-036 | Establish follow-up schedule for corrective actions (90-day plan) | Internal Control Officer | 2024-01-01 – 2024-01-15 | Pending