## Worksheet
Audit Preparation Schedule Planner
Task ID | Task Description | Responsible Party | Start Date | End Date | Status
TP-001 | Review audit scope and objectives | Audit Lead | 2024-04-01 | 2024-04-03 | Pending
TP-002 | Gather financial statements and supporting documents | Finance Team | 2024-04-04 | 2024-04-10 | In Progress
TP-003 | Interview key personnel and department heads | Audit Team | 2024-04-11 | 2024-04-15 | Not Started
TP-004 | Perform preliminary risk assessment | Risk Manager | 2024-04-16 | 2024-04-18 | Pending
TP-005 | Develop detailed audit plan and work programs | Audit Lead | 2024-04-19 | 2024-04-23 | Not Started
TP-006 | Finalize audit schedule and notify stakeholders | Audit Coordinator | 2024-04-24 | 2024-04-25 | Pending
Total Tasks: |  |  |  |  | 6