## Worksheet
Audit Preparation - Schedule Planner
Task | Responsible Party | Start Date | End Date | Status | Notes/Comments
Define audit scope and objectives | Audit Manager | 2024-01-15 | 2024-01-18 | Pending | Review with stakeholders.
Assemble audit team and assign roles | Hiring & HR Coordinator | 2024-01-19 | 2024-01-21 | In Progress | Finalize team members.
Gather supporting documentation from departments | Department Heads | 2024-01-22 | 2024-01-31 | Pending | Submit via secure portal.
Review and validate documentation quality | Audit Lead | 2024-02-01 | 2024-02-05 | Pending | Check completeness and accuracy.
Conduct on-site audit activities | Audit Team | 2024-02-06 | 2024-02-15 | Pending | On-site visits and interviews.
Identify findings and risk assessments | Audit Analysts | 2024-02-16 | 2024-02-18 | Pending | Document all issues.
Prepare draft audit report | Audit Report Writer | 2024-02-19 | 2024-02-23 | Pending | Incorporate feedback.
Review and finalize audit report | Audit Manager & Review Committee | 2024-02-24 | 2024-02-26 | Pending | Final approval needed.
Distribute final audit report to stakeholders | Audit Coordinator | 2024-02-27 | 2024-03-01 | Pending | Email and record delivery.
Follow-up on corrective actions plan | Compliance Officer | 2024-03-02 | 2024-03-15 | Pending | Track implementation progress.
This schedule planner is designed for one-page viewing and printing. All dates are subject to change based on audit requirements and resource availability.