## Worksheet
Audit Preparation Schedule Planner
Task / Activity | Timeline (Planned) |  |  |  | Responsible Person | Status
| Start Date | End Date | Duration (Days) | Milestone
Pre-Audit Planning | 2024-04-01 | 2024-04-05 | 5 | Planning Complete | Jane Smith | Pending
Document Collection & Review | 2024-04-06 | 2024-04-15 | 10 | Data Ready for Audit | Mike Johnson | In Progress
Internal Review Meeting 1 | 2024-04-16 | 2024-04-17 | 2 | Initial Feedback Collected | Jane Smith | Pending
Corrective Action Preparation | 2024-04-18 | 2024-04-25 | 8 | CORR Initiated & Documented | Maria Garcia | In Progress
Internal Review Meeting 2 | 2024-04-26 | 2024-04-27 | 2 | Closed Loop Achieved | Jane Smith | Pending
Final Audit Readiness Check | 2024-04-28 | 2024-04-30 | 3 | Audit Ready for External Review | All Team Members | Pending
Total Duration: |  | 30 days
Template Type:Schedule Planner
Purpose:Audit Preparation
Style/Version:Personal Use – Designed for clarity and ease of use.