## Worksheet
Audit Preparation - Schedule Planner (Planning View)
Task ID | Task Description | Responsible Team | Start Date | Due Date | Status | Priority
ATK-001 | Initial Risk Assessment | Audit Team | 2024-03-05 | 2024-03-15 | In Progress | High
ATK-002 | Gather Financial Documents (Q1) | Finance Department | 2024-03-10 | 2024-03-18 | Pending | High
ATK-003 | Data Validation & Reconciliation | Data Team | 2024-03-16 | 2024-03-25 | Pending | Medium
ATK-004 | Audit Testing (Internal Controls) | Audit Team | 2024-03-18 | 2024-03-31 | Pending | High
ATK-005 | Draft Audit Findings Report | Audit Lead | 2024-03-28 | 2024-04-15 | Pending | Medium
ATK-006 | Management Review Meeting | Senior Management | 2024-04-12 | 2024-04-15 | Pending | High
ATK-007 | Final Audit Report Submission | Audit Team | 2024-04-16 | 2024-04-30 | Pending | High
ATK-008 | Audit Closure & Follow-Up Planning | Audit Manager | 2024-05-01 | 2024-05-15 | Pending | Medium