## Worksheet
Audit Preparation - Schedule Planner
Professional Template ¦ Purpose: Audit Readiness ¦ Version: 2024.01
Task ID | Task Description | Responsible Team | Start Date | Due Date | Status | Budget Allocated (USD)
A001 | Document Collection & Compilation | Finance Department | 2024-03-01 | 2024-03-15 | In Progress | $8,500
A002 | Internal Controls Review | Internal Audit Team | 2024-03-05 | 2024-03-18 | Completed | $15,750
A003 | Compliance Gap Analysis | Legal & Compliance | 2024-03-10 | 2024-03-25 | In Progress | $12,300
A004 | Management Review Meeting (Phase 1) | Executive Management | 2024-03-18 | 2024-03-21 | Delayed | $5,600
A005 | External Auditor Coordination | Audit Lead Team | 2024-03-15 | 2024-03-31 | In Progress | $18,900
A006 | Final Audit Package Preparation | Finance & Audit Support | 2024-03-25 | 2024-04-15 | Completed | $11,800
Total Project Cost: | [5 empty] | $73,850
Generated on:¦ Prepared by Audit Planning Office