## Worksheet
Task | Responsible Party | Due Date | Status | Notes
Review financial statements | Finance Team | 2023-10-15 | Pending | Verify all entries for accuracy
Collect supporting documentation | Department Heads | 2023-10-18 | Pending | Include invoices, receipts, and approvals
Conduct internal control assessment | Audit Committee | 2023-10-20 | Pending | Evaluate risk areas and controls
Review compliance with policies | Compliance Officer | 2023-10-22 | Pending | Ensure adherence to internal guidelines
Prepare audit summary report | Audit Team Lead | 2023-10-25 | Pending | Compile findings and recommendations
Finalize audit documentation | Audit Coordinator | 2023-10-27 | Pending | Complete all required forms and sign-offs