## Worksheet
Audit Preparation - Schedule Planner (Tracking View)
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Progress (%) | Notes/Remarks
TASK-001 | Review Financial Statements Q1 2024 | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | 65% | Initial review complete, awaiting confirmation from accounting team.
TASK-002 | Collect Supporting Documentation for Expenses | Mike Johnson | 2024-04-03 | 2024-04-18 | In Progress | 55% | Received 7 out of 12 required documents.
TASK-003 | Validate Compliance with Internal Policies | Sarah Lee | 2024-04-05 | 2024-04-17 | Pending | 0% | Waiting for policy update approval from legal department.
TASK-004 | Conduct Preliminary Risk Assessment | Daniel Brown | 2024-04-10 | 2024-04-16 | Completed | 100% | Risk assessment finalized and shared with audit committee.
TASK-005 | Prepare Audit Workpapers for Review | Lisa Wong | 2024-04-12 | 2024-04-19 | Pending | 0% | Waiting for finalization of task 3.
Total Tasks: | [5 empty] | 215%