## Worksheet
Audit Preparation - Extended To-Do List
Prepared for Audit Cycle Q4 2024 ¦ Last Updated: October 5, 2024
# | Task Title | Responsible Party | Due Date | Status | Priority | Details/Notes
1 | Gather all financial statements for FY2023 | Finance Team - Jane Doe | Oct 10, 2024 | In Progress | High | Data collection in progress; require confirmation from external auditors.
2 | Review internal control documentation | Compliance Officer - Mark Lee | Oct 15, 2024 | Pending | Medium | Needs input from department heads by Oct 8.
3 | Validate inventory count records | Logistics Manager - Sarah Kim | Oct 12, 2024 | Pending | High | Scheduled physical count on Oct 11; results must be reconciled by EOD.
4 | Update employee access logs to reflect recent changes | IT Admin - James Wilson | Oct 8, 2024 | Completed | Low | All access updates verified and documented.
5 | Compile audit trail for system transactions (Q3) | Data Analyst - Olivia Brown | Oct 18, 2024 | Pending | Medium | Extract from ERP system; validation required before submission.
6 | Schedule preliminary audit meeting with external firm | Audit Lead - Robert Chen | Oct 7, 2024 | Completed | High | Meeting held on Oct 6; agenda and action items shared.
7 | Review and update policy documents (Finance & HR) | Legal Team - Angela Patel | Oct 20, 2024 | Pending | Medium | Policies to be reviewed for compliance with new regulations.
8 | Prepare audit checklist and internal review form | Audit Coordinator - David Miller | Oct 10, 2024 | Completed | Low | Checklist finalized and distributed to team leads.
Note: This template is designed for use in audit preparation workflows. Status updates should be reviewed weekly.