## Worksheet
Annual Weekly Planner - Audit Preparation
Week | Start Date | End Date | Audit Phase | Key Tasks | Status
Week 1 | 2024-01-01 | 2024-01-07 | Planning & Scoping | Define scope, assign team roles, review prior audits | Pending
Week 2 | 2024-01-08 | 2024-01-14 | Data Collection Preparation | Prepare checklists, gather documentation templates, train team members | In Progress
Week 3 | 2024-01-15 | 2024-01-21 | Data Collection Phase I | Gather financial records, process documentation, validate data sources | In Progress
Week 4 | 2024-01-22 | 2024-01-28 | Data Collection Phase II | Collect operational data, conduct interviews, verify compliance logs | Pending
Week 5 | 2024-01-29 | 2024-02-04 | Data Validation & Review | Verify accuracy, resolve discrepancies, update documentation | Pending
Week 6 | 2024-02-05 | 2024-02-11 | Audit Analysis & Findings Drafting | Analyze results, identify risks, draft preliminary findings | Pending
Week 7 | 2024-02-12 | 2024-02-18 | Finding Validation Session | Present findings to stakeholders, collect feedback, revise conclusions | Pending
Week 8 | 2024-02-19 | 2024-02-25 | Draft Report Preparation | Compile final report, include recommendations, prepare appendices | Pending
Week 9 | 2024-02-26 | 2024-03-03 | Management Review & Approval | Submit to leadership for review, incorporate feedback, finalize report | Pending
Week 10 | 2024-03-04 | 2024-03-10 | Final Reporting & Distribution | Distribute report to relevant parties, schedule follow-up meetings | Pending