## Worksheet
Weekly Audit Preparation Planner
Day & Date | Task/Activity | Responsible Person | Status | Progress (%) | Notes/Comments | Attachments/References
Monday, Apr 1, 2024 | Review financial statements for Q1 | Jane Doe | Pending | 0% | Initial draft ready by EOD. | Document 1.pdf
Tuesday, Apr 2, 2024 | Conduct internal control assessment | John Smith | In Progress | 60% | Completed risk evaluation. | RiskAssessment.xlsx
Wednesday, Apr 3, 2024 | Gather supporting documentation | Lisa Brown | Pending | 0% | Waiting for departmental input. | Docs_Req.xlsx
Thursday, Apr 4, 2024 | Perform reconciliations | Mike Johnson | In Progress | 80% | All bank statements reviewed. | Recon_Report.docx
Friday, Apr 5, 2024 | Prepare audit summary report draft | Jane Doe | Pending | 0% | Will begin after validation. | Summary_Draft.docx
Weekly Summary | [5 empty] | 100% Complete (Target)