## Worksheet
Weekly Planner - Audit Preparation (Client View)
Day & Date | Task / Activity | Responsible Party | Status | Supporting Documents | Notes / Remarks
Monday, Apr 01 2024 | Clean up financial records for Q1 2024 | Finance Team | Pending | Receipts, Invoices, GL Reports | Ensure all entries are coded correctly.
Tuesday, Apr 02 2024 | Review fixed asset register and depreciation schedule | F&A Lead | In Progress | Asset List, Depreciation Schedule (Excel) | Verify accuracy of asset life spans.
Wednesday, Apr 03 2024 | Schedule internal audit meeting with stakeholders | Audit Coordinator | Pending | Meeting Agenda (Draft) | Email invites sent to all departments.
Thursday, Apr 04 2024 | Prepare trial balance and reconciliations | Finance Team | In Progress | Trial Balance Report, Bank Recs | Finalize by end of day.
Friday, Apr 05 2024 | Cleanup and submit audit packet to external auditor | Audit Manager | Pending | All documents uploaded via secure portal | Double-check file naming convention.
Saturday, Apr 06 2024 | Review feedback from internal audit walkthrough | Audit Lead | Pending | Feedback Summary Document | Address all observations before final submission.
Sunday, Apr 07 2024 | Prep for next week’s audit kickoff session | All Teams | Pending | Meeting Prep Kit (Docs & Slides) | No action required unless notified.