## Worksheet
Audit Preparation - Weekly Planner
Week 1 - January 1 - January 7, 2024
Day | Task | Owner | Status | Prioritization | Notes / Comments
Monday Jan 1 | Review audit scope and objectives with team lead | Alice Johnson |  | HighMediumLow | Ensure all stakeholders are aligned on audit goals.
Tuesday Jan 2 | Gather financial documentation for Q4 2023 | Robert Smith |  | HighMediumLow | Include all bank statements and revenue reports.
Wednesday Jan 3 | Review internal controls framework | Lisa Chen |  | MediumHighLow | Focus on access controls and approval workflows.
Thursday Jan 4 | Create preliminary risk assessment matrix | Alice Johnson |  | HighMediumLow | Use standardized risk rating scale (1-5).
Friday Jan 5 | Weekly planning meeting and progress review | All Team Members |  | MediumHighLow | Discuss challenges and adjust plan if needed.
Saturday Jan 6 | Review notes from week | Alice Johnson |  | Low | Catch up on any pending items.
Sunday Jan 7 | Prepare materials for Monday meeting | All Team Members |  | Medium | Organize documents and finalize agenda.
Week 2 - January 8 - January 14, 2024
Day | Task | Owner | Status | Prioritization | Notes / Comments
Monday Jan 8 | Conduct walkthrough of procurement process | Robert Smith |  | HighMediumLow | Interview procurement staff and review approval logs.
Tuesday Jan 9 | Test cash handling procedures | Lisa Chen |  | HighMediumLow | Observe actual transactions and verify controls.
Wednesday Jan 10 | Review compliance with SOX requirements | Alice Johnson |  | HighMediumLow | Ensure documentation supports audit trail.
Thursday Jan 11 | Document findings and prepare draft report section | All Team Members |  | MediumHighLow | Use template provided by audit team lead.
Friday Jan 12 | Send draft findings to supervisor for review | Alice Johnson |  | HighMediumLow | Include supporting evidence and references.
Saturday Jan 13 | Review feedback from supervisor | Alice Johnson |  | Medium | Revise findings based on comments.
Sunday Jan 14 | Plan for next week's audit activities | All Team Members |  | Medium | Outline key objectives and assign tasks.