## Worksheet
Section | Objective | Key Activities | Resources Required | Timeline | Ownership
Market Research | Understand target market needs, preferences, and pain points. | Conduct surveys, focus groups, and competitor analysis. | Research tools, team members (research analysts), budget allocation. | Month 1–2 | Marketing Team
Product Development | Develop and refine a product/service solution based on research. | Prototyping, testing, feedback loops, iteration. | Design software tools, development team, QA resources. | Month 3–5 | R&D & Product Team
Go-to-Market Strategy | Determine how and where to launch the product/service. | Channel selection, pricing model, promotional campaigns. | Marketing budget, sales team, digital assets. | Month 6 | Sales & Marketing Team
Operations Setup | Establish efficient workflows, processes, and systems. | Process mapping, team structure definition, tool implementation. | ERP software, workflow tools, operational staff. | Month 7–8 | Operations Team
Performance Monitoring | Evaluate KPIs and adjust operations as needed. | Monthly reviews, data collection, reporting dashboards. | Analytics tools, team access to performance metrics. | Ongoing (from Month 9 onwards) | Operations & Strategy Team