## Worksheet
Section | Key Objective | Current Status | Target Date | Responsible Party | Progress (%) | Notes
Market Research & Analysis | Complete comprehensive analysis of target markets and customer behavior. | In Progress | 2024-05-30 | Marketing Team | 65% | Initial data collection completed; final report pending review.
Supply Chain Setup | Establish reliable supplier agreements and logistics partners. | Pending Initiation | 2024-06-15 | Operations Director | 0% | Vendor shortlist under review.
Budget Allocation | Finalize annual operational budget with ROI projections. | Draft Phase | 2024-06-30 | Finance Department | 40% | Preliminary figures approved by CFO.
Staff Onboarding | Recruit and onboard core team members for Q2 launch. | Scheduled | 2024-07-10 | HR Team | 15% | First round of interviews completed.
Process Optimization | Map and streamline key business operations workflows. | Planning Phase | 2024-08-15 | Operations Team | 30% | Workflow diagrams in development.