## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research Initiation | 2024-03-01 | 2024-03-15 | 15 | Marketing Team | In Progress
Product Requirements Finalization | 2024-03-16 | 2024-04-05 | 21 | Product Management | Planned
Design & Prototyping Phase | 2024-04-06 | 2024-05-15 | 41 | Design Team | Not Started
Development & Coding Sprint | 2024-05-16 | 2024-07-15 | 61 | Engineering Team | Planned
QA Testing & Bug Resolution | 2024-07-16 | 2024-08-15 | 31 | Quality Assurance | Not Started
Go-Live & Deployment | 2024-08-16 | 2024-08-31 | 16 | Operations Team | Planned
Post-Launch Review & Reporting | 2024-09-01 | 2024-09-15 | 15 | Business Operations | Not Started