## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Project Initiation | 2024-03-01 | 2024-03-15 | 15 | Operations Director | Completed
Market Analysis | 2024-03-16 | 2024-04-10 | 35 | Business Analysts | In Progress
Process Optimization | 2024-04-11 | 2024-05-30 | 50 | Operations Team | Planned
Resource Allocation | 2024-05-31 | 2024-06-15 | 15 | HR & Finance | Scheduled
Performance Review | 2024-06-16 | 2024-07-10 | 35 | Operations Manager | Pending Approval