## Worksheet
Task | Start Date | End Date | Duration | Responsible Party | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 days | Marketing Team | On Track
Product Development Planning | 2024-03-16 | 2024-04-10 | 35 days | Product Management | In Progress
Prototype Design & Review | 2024-04-11 | 2024-05-05 | 35 days | Engineering Team | Pending Approval
Internal Testing & Quality Assurance | 2024-05-06 | 2024-05-31 | 26 days | QA Department | Not Started
Client Presentation & Feedback | 2024-06-01 | 2024-06-15 | 15 days | Sales & Client Relations | Planned
Go-Live Preparation & Rollout | 2024-06-16 | 2024-07-15 | 30 days | Operations & IT | Not Started
Business Operations – Client View Gantt Chart