## Worksheet
Task | Start Date | End Date | Duration | Responsible
Project Initiation | 2024-01-01 | 2024-01-15 | 15 days | John Smith
Market Research | 2024-01-16 | 2024-02-15 | 30 days | Sarah Lee
Product Design | 2024-02-16 | 2024-03-31 | 46 days | Mike Chen
Development Phase | 2024-04-01 | 2024-06-30 | 91 days | Team A
Testing & QA | 2024-07-01 | 2024-08-15 | 45 days | Lisa Wang
Launch Preparation | 2024-08-16 | 2024-09-30 | 45 days | David Kim
Go-Live & Monitoring | 2024-10-01 | 2024-10-31 | 31 days | Operations Team