## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Market Research & Analysis | 2024-04-01 | 2024-04-05 | 5 | Jane Smith | Completed
Product Requirements Definition | 2024-04-06 | 2024-04-10 | 5 | Mark Johnson | In Progress
UI/UX Design Finalization | 2024-04-11 | 2024-04-15 | 5 | Lisa Chen | Planned
Development Phase (Daily Sprints) | 2024-04-16 | 2024-05-15 | 30 | Team A (Dev) | Not Started
QA Testing & Bug Fixing | 2024-05-16 | 2024-05-31 | 16 | Sarah Lee | Planned
Deployment & Go-Live | 2024-06-01 | 2024-06-05 | 5 | David Brown | Not Started