## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Market Research Initiation | 2024-03-01 | 2024-03-15 | 15 days | Marketing Team | On Track
Product Line Development | 2024-03-16 | 2024-05-31 | 76 days | Product Management | In Progress
Sales Strategy Finalization | 2024-04-01 | 2024-04-30 | 30 days | Sales Department | Delayed
Budget Approval & Allocation | 2024-05-01 | 2024-05-15 | 15 days | Finance Team | On Track
Operational Rollout Plan | 2024-06-01 | 2024-08-31 | 91 days | Operations Leadership | Planned