## Worksheet
Task | Start Date | End Date | Duration (Days) | Assignee | Status | Progress (%)
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | Jane Smith | On Track | 90%
Product Requirement Finalization | 2024-03-16 | 2024-04-05 | 21 | Mark Johnson | In Progress | 65%
Procurement & Vendor Onboarding | 2024-04-06 | 2024-04-30 | 25 | Sarah Lee | On Track | 100%
Internal Process Review | 2024-05-01 | 2024-05-15 | 15 | David Brown | Pending Approval | 30%
Budget Finalization & Sign-off | 2024-05-16 | 2024-05-31 | 16 | Lisa Wong | On Track | 85%