## Worksheet
Task ID | Task Name | Start Date | End Date
T001 | Project Initiation & Planning | 2024-01-15 | 2024-01-31
T002 | Market Research & Analysis | 2024-02-01 | 2024-02-15
T003 | Resource Allocation & Team Formation | 2024-02-16 | 2024-03-01
T004 | Process Design & Workflow Mapping | 2024-03-02 | 2024-03-15
T005 | System Integration Planning | 2024-03-16 | 2024-04-10
T006 | Operations Risk Assessment | 2024-04-11 | 2024-04-25
T007 | Training & Change Management | 2024-04-26 | 2024-05-15
T008 | Performance Monitoring Setup | 2024-05-16 | 2024-06-30