## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | Marketing Team | On Track
Product Development Planning | 2024-03-16 | 2024-04-10 | 35 | R&D Department | In Progress
Supply Chain Setup | 2024-04-11 | 2024-05-15 | 45 | Operations Team | Pending Start
Quality Assurance Testing | 2024-05-16 | 2024-06-10 | 35 | QA Department | Not Started
Pilot Launch (Phase 1) | 2024-06-11 | 2024-07-15 | 35 | Operations & Sales | Planned
Full-Scale Rollout Strategy | 2024-07-16 | 2024-08-31 | 56 | Executive Leadership | Not Started