## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Manager
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | On Track | Sarah Johnson
Product Development Planning | 2024-03-16 | 2024-04-10 | 25 | In Progress | Michael Chen
Vendor Onboarding & Contracts | 2024-04-11 | 2024-04-30 | 30 | Scheduled | Lisa Park
Pilot Launch (Regional) | 2024-05-01 | 2024-05-31 | 31 | Not Started | David Reed
Full-Scale Rollout Strategy | 2024-06-01 | 2024-07-31 | 61 | Planned | Emma Torres
Performance Review & Optimization | 2024-08-01 | 2024-08-31 | 31 | Not Started | James Wilson