## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status
Business Strategy Review | 2024-01-01 | 2024-01-15 | 15 | Operations Director | In Progress
Process Optimization Workshop | 2024-01-16 | 2024-01-31 | 15 | Process Analysts | Planned
Resource Allocation Plan | 2024-02-01 | 2024-02-14 | 14 | HR & Finance Team | Pending Approval
Budget Review and Forecasting | 2024-02-15 | 2024-03-01 | 17 | Finance Manager | Scheduled
Performance KPI Setup | 2024-03-02 | 2024-03-15 | 14 | Operations Team | Not Started
System Integration Planning | 2024-03-16 | 2024-04-10 | 35 | IT & Operations Lead | In Planning
Business Operations – Gantt Chart (Multi-Page Template)