## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | Marketing Team | On Track
Product Development Planning | 2024-03-16 | 2024-04-10 | 35 | Product Team | In Progress
Pilot Launch & Feedback Collection | 2024-04-11 | 2024-05-05 | 35 | Operations & Sales | Not Started
Full-Scale Deployment | 2024-05-06 | 2024-06-30 | 65 | Executive Leadership | Planned
Post-Launch Review & Optimization | 2024-07-01 | 2024-07-31 | 31 | Operations Team | Not Started
Business Operations Gantt Chart – Office Use