## Worksheet
Activity | Start Date | End Date | Duration (Days) | Status
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | In Progress
Process Mapping & Workflow Design | 2024-03-16 | 2024-04-05 | 21 | Pending Approval
Resource Allocation Planning | 2024-04-06 | 2024-04-18 | 13 | Not Started
Operational KPI Setup & Monitoring | 2024-04-19 | 2024-05-31 | 43 | Planned
Staff Training & Onboarding | 2024-06-01 | 2024-06-15 | 15 | Scheduled
Quarterly Business Review (Q2) | 2024-07-01 | 2024-07-15 | 15 | Not Started
Gantt Bar Legend: Green = In Progress, Blue = Scheduled, Gray = Not Started